# 2022Implementation Plan Strategy

**Date Revised:**

**For information about this plan:**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | Organization | **Phone** | **Email** |

|  |  |  |  |
| --- | --- | --- | --- |
| Debi Pestotnik | Boone County Public Health/Home Care Services of Boone County Hospital | (515) 432-1127 | dpestotnik@bchmail.org |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Topic 1Mental Health

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Mental Health*Goal 1

|  |
| --- |
| By 2023 Boone County Hospital will have an additional safe room added to the Med/Surg unit |
| Alignment with National Plans  |
| Alignment with State/Other Plans  |
|

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Mental Health*Objective 1.1

|  |
| --- |
| Reduce the number of mental health holds in the ER by 2024 |
| Baseline Year2022 | Baseline Value  | Target Year2025 | Target Value  |
| Data Source and LocationBoone County Hospital ER stats |
|  |
|  |

 |

 |

 |
| *Mental Health*Goal 2

|  |
| --- |
| Explore and secure a partnership with a mental health provider for outreach clinic. |
| Alignment with National Plans  |
| Alignment with State/Other Plans  |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Mental Health*Objective 2.1

|  |
| --- |
| By 2023 Boone County Hospital will have an agreement with a partner to provide Mental Health Counseling to the adult population |
| Baseline Year2023 | Baseline Value0 | Target Year2025 | Target Value1 |
| Data Source and LocationData will be based on numbers once a partnership is secured. |
|  |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Mental Health*Strategy 2.1-1

|  |
| --- |
| Research options for Mental Health Counseling services utilized by other facilities, set up meetings to interview and investigate options of services offered, extend offer to provider if found to develop a partnership with. |
| Strategy Source and LocationNew |
| Strategy Type: Professional/provider-focused |
| Who's ResponsibleBoone County Hospital | Target Date4/1/2023 |

 |

 |

 |

 |

 |
| *Mental Health*Goal 3

|  |
| --- |
| Boone County Hospital will develop and have an active Mental Health Advisory Council/Board |
| Alignment with National Plans  |
| Alignment with State/Other Plans  |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Mental Health*Objective 3.1

|  |
| --- |
| By September 2024 Boone County Hospital will have an active Mental Health Advisory Council/Board |
| Baseline Year2022 | Baseline ValueNo board formulated at this time | Target Year2024 | Target ValueActive Board Status |
| Data Source and LocationPresence of Board Meetings and Minutes |
|  |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Mental Health*Strategy 3.1-1

|  |
| --- |
| Research what is currently in place at state and county levels, what their objectives are, who are the members on the Boards, what is their mission and vision |
| Strategy Source and Location  |
| Strategy Type: Professional/provider-focused |
| Who's ResponsibleBoone County Hospital | Target Date1/9/2024 |

 |

 |

 |

 |

 |

 |

 |
| Topic 2Affordability and Presence of Healthcare Services

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Affordability and Presence of Healthcare Services*Goal 1

|  |
| --- |
| Boone County Hospital will sponsor a Resource Fair in 2024 |
| Alignment with National Plans  |
| Alignment with State/Other Plans  |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Affordability and Presence of Healthcare Services*Objective 1.1

|  |
| --- |
| By November 2024 Boone County Hospital will sponsor a resource fair focused on Services that are available to residents of Boone County to increase public awareness with an attendance of 250 people or greater, and 48 vendors or more |
| Baseline Year2016 | Baseline Value225 | Target Year2024 | Target Value250+ |
| Data Source and LocationNumbers in attendance, look at numbers of wellness labs completed, Utilization of after hours clinic |
|  |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Affordability and Presence of Healthcare Services*Strategy 1.1-1

|  |
| --- |
| Meet and form steering committee of key people from a variety of areas, establish a venue, extend invitations to participate, advertise, seek and find sponsors. |
| Strategy Source and Location2016 resource fair information |
| Strategy Type: Community-focused |
| Who's ResponsibleBoone County Hospital and partners | Target Date11/1/2024 |

 |

 |

 |

 |

 |

 |

 |
| Topic 3Cancer, Heart Disease

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Cancer, Heart Disease*Goal 1

|  |
| --- |
| The number of preventative screenings preformed at Boone County Hospital will increase by 10% |
| Alignment with National Plans  |
| Alignment with State/Other Plans  |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Cancer, Heart Disease*Objective 1.1

|  |
| --- |
| By 2025 the Number of Wellness labs completed at BCH will increase by 10% |
| Baseline Year2022 | Baseline Value1811 | Target Year2025 | Target Value1990 |
| Data Source and LocationStats on labs completed per BCH lab reports |
|  |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Cancer, Heart Disease*Strategy 1.1-1

|  |
| --- |
| Education to public and providers about the wellness labs available at the Boone County Hospital, promotion of the Wellness labs available at the Resource fair when it is held |
| Strategy Source and Location  |
| Strategy Type: Community-focused |
| Who's ResponsibleBoone County Hospital Public Relations Director, Providers of Boone County Hospital, Assistant Administrator of Providers(provide education) | Target Date12/31/2024 |

 |

 |

 |

 |

 |
| *Cancer, Heart Disease*Goal 2

|  |
| --- |
| Number of PSA tests completed will increase by 10% |
| Alignment with National Plans  |
| Alignment with State/Other Plans  |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Cancer, Heart Disease*Objective 2.1

|  |
| --- |
| By 2025 PSA tests completed will increase at Boone County Hospital lab 10% |
| Baseline Year2022 | Baseline Value  | Target Year2025 | Target Value1360 |
| Data Source and LocationBCH lab stats |
|  |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Cancer, Heart Disease*Strategy 2.1-1

|  |
| --- |
| Education to public and providers about the PSA wellness labs available at the Boone County Hospital, promotion of the Wellness labs available at the Resource fair when it is held |
| Strategy Source and Location  |
| Strategy Type: Community-focused |
| Who's ResponsibleBoone County Hospital Public Relations Director, Providers of Boone County Hospital, Assistant Administrator of Providers(provide education) | Target Date12/31/2024 |

 |

 |

 |

 |

 |
| *Cancer, Heart Disease*Goal 3

|  |
| --- |
| Mammograms completed at BCH will increase by 10% |
| Alignment with National Plans  |
| Alignment with State/Other Plans  |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Cancer, Heart Disease*Objective 3.1

|  |
| --- |
| By 2025 Mammograms completed by BCH will increase by 10% |
| Baseline Year2022 | Baseline Value1625 | Target Year2025 | Target Value1,790 |
| Data Source and LocationRadiology stats from BCH |
|  |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Cancer, Heart Disease*Strategy 3.1-1

|  |
| --- |
| Education and Advertising promoting the Hospital Mammography program, recall letters, promotion of the Wellness labs available at the Resource fair when it is held |
| Strategy Source and Location  |
| Strategy Type: Community-focused |
| Who's ResponsiblePublic Relations Director, Radiology | Target Date  |

 |

 |

 |

 |

 |

 |

 |
| Topic 4Women’s Health

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Womens Health*Goal 1

|  |
| --- |
| Boone County Hospital will develop a Womens Health Program, grow the volume of OB services and Womens health services |
| Alignment with National Plans  |
| Alignment with State/Other Plans  |
|

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Womens Health*Objective 1.1

|  |
| --- |
| By 2025 the number of births at Boone County Hospital will increase by 10% |
| Baseline Year2022 | Baseline Value89 | Target Year2025 | Target Value100 |
| Data Source and LocationBoone County Hospital OB statistics |
|  |
|  |

 |
| *Womens Health*Objective 1.2

|  |
| --- |
| By 2025 Number of cervical screenings will increase by 10% |
| Baseline Year2022 | Baseline Value427 | Target Year2025 | Target Value470 |
| Data Source and Location  |
|  |
|

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Womens Health*Strategy 1.2-1

|  |
| --- |
| Advertising to promote women's health and services |
| Strategy Source and Location  |
| Strategy Type: Community-focused |
| Who's ResponsiblePublic Relations | Target Date12/31/2024 |

 |

 |

 |

 |

 |

 |

 |